## Instructions
DPDPOS - Three-Developer Build Tracker
How to use this workbook throughout the build.
This workbook has one tab per tracking concern. All tabs are cross-referenced by Module / Feature name - keep those names
identical across tabs so the summary formulas already built into each sheet keep working.
COLOR LEGEND
- Yellow-filled cells = update these as work progresses (Status, Completion %, Blockers, Ready/Integrated/Tested flags, PR/Merge status).
- Blue Owner cells = Developer A modules. Green Owner cells = Developer B modules. Orange Owner cells = Developer C modules.
- All other cells are fixed planning data agreed at architecture sign-off - edit only if the architecture itself changes.
TAB GUIDE
1. Developer Assignment - who owns each feature/module, its dependency, and its integration branch.
2. Feature Progress - live status: start/target dates, % complete, current stage, blockers. Update weekly.
3. Integration Tracker - per-module readiness gate: integrated into develop yet, tested end-to-end yet.
4. API Tracker - every planned REST endpoint, its owning module/developer, and build status.
5. Database Tracker - every Prisma/Postgres table, its owning module/developer, and migration status.
6. Event & Queue Tracker - every domain event and BullMQ queue, its publisher, its consumer(s), and status.
7. Merge Checklist - one row per PR/branch. Add a new row for every branch opened; do not overwrite history.
RECOMMENDED CADENCE
- Update 'Feature Progress' and 'Merge Checklist' at the end of every working day.
- Review 'Integration Tracker' at the start of every week to confirm the current integration phase is on track.
- Treat 'Developer Assignment', 'API Tracker', and 'Database Tracker' as the source of truth for scope - if a table or
endpoint isn't listed there, confirm ownership with the Lead Architect before building it.

## Developer Assignment
Feature | Module | Owner | Dependency | Status | Branch
Authentication & Session Management | auth | Developer A | users, roles | Not Started | feature/a/auth
User Management | users | Developer A | organizations, roles | Not Started | feature/a/users
Role & Permission Management (RBAC) | roles | Developer A | organizations | Not Started | feature/a/roles
Organization / Tenant Management | organizations | Developer A | (root - no dependency) | Not Started | feature/a/organizations
Department Management | departments | Developer A | organizations, users | Not Started | feature/a/departments
Framework Builder & Roadmap | framework | Developer A | organizations | Not Started | feature/a/framework
Control Library | controls | Developer A | framework | Not Started | feature/a/controls
Obligation / Requirement Register | requirements | Developer A | framework, controls | Not Started | feature/a/requirements
Data Inventory (Assets & Processing Activities) | inventory | Developer B | organizations, departments | Not Started | feature/b/inventory
Notice & Consent Management | consent | Developer B | organizations, inventory | Not Started | feature/b/consent
Data Principal Rights Requests | rights | Developer B | organizations, users | Not Started | feature/b/rights
Validation / Rule Engine | validations | Developer B | framework, controls (read-only), inventory, consent, rights, evidence (read-only) | Not Started | feature/b/validations
Violation Management | violations | Developer B | validations | Not Started | feature/b/violations
Remediation Task Tracking | remediation | Developer B | violations | Not Started | feature/b/remediation
Evidence Vault | evidence | Developer C | organizations, controls | Not Started | feature/c/evidence
Report Generator & Board Packs | reports | Developer C | validations, violations, evidence, analytics | Not Started | feature/c/reports
Analytics & Compliance Dashboards | analytics | Developer C | validations, violations, evidence | Not Started | feature/c/analytics
Notification System | notifications | Developer C | organizations, users, events (all modules) | Not Started | feature/c/notifications
AI Assistance (Summarize / Draft / Explain) | ai | Developer C | framework, validations, evidence (read via events) | Not Started | feature/c/ai
Audit Logging | audit | Developer C | events (all modules) | Not Started | feature/c/audit
Summary - modules per developer
Developer A | 8
Developer B | 6
Developer C | 6

## Feature Progress
Feature | Start Date | Target Date | Completion % | Current Stage | Blockers
Authentication & Session Management | 2026-07-27 | 2026-08-03 | 0% | Not Started | None
User Management | 2026-07-27 | 2026-07-31 | 0% | Not Started | None
Role & Permission Management (RBAC) | 2026-07-27 | 2026-07-31 | 0% | Not Started | None
Organization / Tenant Management | 2026-07-27 | 2026-07-30 | 0% | Not Started | None
Department Management | 2026-07-31 | 2026-08-04 | 0% | Not Started | Waiting on Organizations core (same owner)
Framework Builder & Roadmap | 2026-08-10 | 2026-08-19 | 0% | Not Started | None
Control Library | 2026-08-17 | 2026-08-24 | 0% | Not Started | Waiting on Framework module
Obligation / Requirement Register | 2026-08-19 | 2026-08-26 | 0% | Not Started | Waiting on Framework module
Data Inventory (Assets & Processing Activities) | 2026-07-27 | 2026-08-07 | 0% | Not Started | None
Notice & Consent Management | 2026-08-03 | 2026-08-12 | 0% | Not Started | Waiting on Inventory (asset/purpose reference)
Data Principal Rights Requests | 2026-08-05 | 2026-08-14 | 0% | Not Started | None
Validation / Rule Engine | 2026-08-12 | 2026-08-26 | 0% | Not Started | Waiting on Framework & Controls read interfaces (Dev A)
Violation Management | 2026-08-26 | 2026-09-04 | 0% | Not Started | Waiting on Validations (ValidationFailed event)
Remediation Task Tracking | 2026-08-31 | 2026-09-04 | 0% | Not Started | Waiting on Violations
Evidence Vault | 2026-07-27 | 2026-08-10 | 0% | Not Started | None
Report Generator & Board Packs | 2026-08-24 | 2026-09-11 | 0% | Not Started | Waiting on Validations/Violations/Evidence/Analytics data
Analytics & Compliance Dashboards | 2026-08-24 | 2026-09-11 | 0% | Not Started | Waiting on Validations/Violations/Evidence data
Notification System | 2026-08-05 | 2026-08-19 | 0% | Not Started | Handlers blocked on each producer's events landing
AI Assistance (Summarize / Draft / Explain) | 2026-08-05 | 2026-08-24 | 0% | Not Started | Waiting on Framework/Validations/Evidence read interfaces
Audit Logging | 2026-07-29 | 2026-09-04 | 0% | Not Started | Waiting on event contracts from every module (incremental)
Overall completion | 0%

## Integration Tracker
Module | Depends On | Ready For Integration | Integrated | Tested
auth | users, roles | No | No | No
users | organizations, roles | No | No | No
roles | organizations | No | No | No
organizations | (root - no dependency) | No | No | No
departments | organizations, users | No | No | No
framework | organizations | No | No | No
controls | framework | No | No | No
requirements | framework, controls | No | No | No
inventory | organizations, departments | No | No | No
consent | organizations, inventory | No | No | No
rights | organizations, users | No | No | No
validations | framework, controls (read-only), inventory, consent, rights, evidence (read-only) | No | No | No
violations | validations | No | No | No
remediation | violations | No | No | No
evidence | organizations, controls | No | No | No
reports | validations, violations, evidence, analytics | No | No | No
analytics | validations, violations, evidence | No | No | No
notifications | organizations, users, events (all modules) | No | No | No
ai | framework, validations, evidence (read via events) | No | No | No
audit | events (all modules) | No | No | No
Ready for integration (count) | 0
Integrated (count) | 0
Tested (count) | 0

## API Tracker
Endpoint | Module | Owner | Status
POST /api/v1/auth/login | auth | Developer A | Not Started
POST /api/v1/auth/refresh | auth | Developer A | Not Started
POST /api/v1/auth/logout | auth | Developer A | Not Started
POST /api/v1/auth/mfa/verify | auth | Developer A | Not Started
GET /api/v1/users | users | Developer A | Not Started
POST /api/v1/users | users | Developer A | Not Started
PATCH /api/v1/users/:id | users | Developer A | Not Started
GET /api/v1/roles | roles | Developer A | Not Started
POST /api/v1/roles | roles | Developer A | Not Started
PATCH /api/v1/roles/:id/permissions | roles | Developer A | Not Started
POST /api/v1/organizations | organizations | Developer A | Not Started
GET /api/v1/organizations/:id | organizations | Developer A | Not Started
PATCH /api/v1/organizations/:id | organizations | Developer A | Not Started
GET /api/v1/departments | departments | Developer A | Not Started
POST /api/v1/departments | departments | Developer A | Not Started
POST /api/v1/framework/generate | framework | Developer A | Not Started
GET /api/v1/framework/roadmap | framework | Developer A | Not Started
GET /api/v1/controls | controls | Developer A | Not Started
POST /api/v1/controls | controls | Developer A | Not Started
PATCH /api/v1/controls/:id | controls | Developer A | Not Started
GET /api/v1/requirements | requirements | Developer A | Not Started
POST /api/v1/requirements | requirements | Developer A | Not Started
GET /api/v1/data-assets | inventory | Developer B | Not Started
POST /api/v1/data-assets | inventory | Developer B | Not Started
GET /api/v1/processing-activities | inventory | Developer B | Not Started
GET /api/v1/notices | consent | Developer B | Not Started
POST /api/v1/consent-records | consent | Developer B | Not Started
POST /api/v1/consent-records/:id/withdraw | consent | Developer B | Not Started
POST /api/v1/data-subject-requests | rights | Developer B | Not Started
GET /api/v1/data-subject-requests | rights | Developer B | Not Started
PATCH /api/v1/data-subject-requests/:id | rights | Developer B | Not Started
POST /api/v1/validations/run | validations | Developer B | Not Started
GET /api/v1/validations/results | validations | Developer B | Not Started
GET /api/v1/violations | violations | Developer B | Not Started
PATCH /api/v1/violations/:id/assign | violations | Developer B | Not Started
PATCH /api/v1/violations/:id/close | violations | Developer B | Not Started
GET /api/v1/remediation-tasks | remediation | Developer B | Not Started
PATCH /api/v1/remediation-tasks/:id | remediation | Developer B | Not Started
POST /api/v1/evidence | evidence | Developer C | Not Started
GET /api/v1/evidence/:id | evidence | Developer C | Not Started
PATCH /api/v1/evidence/:id/approve | evidence | Developer C | Not Started
POST /api/v1/reports/generate | reports | Developer C | Not Started
GET /api/v1/reports | reports | Developer C | Not Started
GET /api/v1/analytics/dashboard | analytics | Developer C | Not Started
GET /api/v1/analytics/compliance-score | analytics | Developer C | Not Started
GET /api/v1/notifications | notifications | Developer C | Not Started
PATCH /api/v1/notifications/preferences | notifications | Developer C | Not Started
POST /api/v1/ai/explain | ai | Developer C | Not Started
POST /api/v1/ai/draft-notice | ai | Developer C | Not Started
GET /api/v1/audit-logs | audit | Developer C | Not Started
GET /api/v1/audit-logs/export | audit | Developer C | Not Started

## Database Tracker
Table | Module | Owner | Migration Complete
organizations | organizations | Developer A | No
users | users | Developer A | No
roles | roles | Developer A | No
departments | departments | Developer A | No
data_assets | inventory | Developer B | No
processing_activities | inventory | Developer B | No
notices | consent | Developer B | No
consent_records | consent | Developer B | No
data_subject_requests | rights | Developer B | No
validation_rules | validations | Developer B | No
validation_runs | validations | Developer B | No
validation_results | validations | Developer B | No
violations | violations | Developer B | No
remediation_tasks | remediation | Developer B | No
evidence_files | evidence | Developer C | No
reports | reports | Developer C | No
notifications | notifications | Developer C | No
ai_usage_logs | ai | Developer C | No
audit_logs | audit | Developer C | No
outbox_events | (shared infra) | Developer A | No

## Event & Queue Tracker
Event/Queue | Publisher | Consumer | Status
OrganizationCreated | organizations (Dev A) | notifications (Dev C), audit (Dev C) | Planned
UserInvited | users (Dev A) | notifications (Dev C), audit (Dev C) | Planned
RoleAssigned | roles (Dev A) | audit (Dev C) | Planned
FrameworkPublished | framework (Dev A) | analytics (Dev C), audit (Dev C) | Planned
DataAssetCreated | inventory (Dev B) | validations (Dev B), audit (Dev C) | Planned
ConsentRecorded | consent (Dev B) | validations (Dev B), audit (Dev C) | Planned
ConsentWithdrawn | consent (Dev B) | validations (Dev B), notifications (Dev C), audit (Dev C) | Planned
RightsRequestSubmitted | rights (Dev B) | notifications (Dev C), audit (Dev C) | Planned
RightsRequestClosed | rights (Dev B) | audit (Dev C), analytics (Dev C) | Planned
ValidationCompleted | validations (Dev B) | analytics (Dev C), audit (Dev C) | Planned
ValidationFailed | validations (Dev B) | violations (Dev B), ai (Dev C), audit (Dev C) | Planned
ViolationCreated | violations (Dev B) | notifications (Dev C), ai (Dev C), audit (Dev C), analytics (Dev C) | Planned
ViolationClosed | violations (Dev B) | audit (Dev C), analytics (Dev C) | Planned
RemediationTaskAssigned | remediation (Dev B) | notifications (Dev C), audit (Dev C) | Planned
RemediationCompleted | remediation (Dev B) | audit (Dev C), analytics (Dev C) | Planned
EvidenceUploaded | evidence (Dev C) | validations (Dev B, evidence_required_flag), audit (Dev C) | Planned
EvidenceApproved | evidence (Dev C) | audit (Dev C), analytics (Dev C) | Planned
ReportRequested | reports (Dev C) | report-queue (internal) | Planned
ReportGenerated | reports (Dev C) | notifications (Dev C), audit (Dev C) | Planned
AiSummaryReady | ai (Dev C) | notifications (Dev C) | Planned
validation-queue | validations (Dev B) | validation worker pool | Planned
report-queue | reports (Dev C) | report worker pool | Planned
notification-queue | notifications (Dev C) | notification worker pool | Planned
ai-queue | ai (Dev C) | ai worker pool | Planned
audit-queue | audit (Dev C) | audit worker pool | Planned
retention-queue | shared infra (Dev A) | consumed by Dev B and Dev C retention jobs | Planned
export-queue | reports (Dev C) | export worker pool | Planned
event-relay-queue | shared infra / outbox (Dev A) | internal outbox relay | Planned

## Merge Checklist
Branch | Reviewer | PR Status | Merge Status | Notes
feature/shared/contracts-kickoff | Developer A, Developer B, Developer C | Open | Not Merged | Phase 0 shared interface contracts - must merge first, blocks everyone
feature/a/organizations/tenant-crud | Developer B, Developer C | Not Started | Not Merged | Blocks tenant-scoped repositories for both other streams
feature/a/auth/contract-and-guard | Developer B, Developer C | Not Started | Not Merged | RequestContext + PermissionGuard interface; full JWT/MFA follows in a later PR
feature/a/roles/permission-catalog | Developer B | Not Started | Not Merged | Freezes the resource:action permission-string catalog
feature/a/departments/core-crud | Developer B | Not Started | Not Merged | Must land before inventory migration (FK dependency)
feature/b/inventory/core-crud | Developer A | Not Started | Not Merged | Independent of Dev A after departments FK lands
feature/c/evidence/core-crud | Developer A | Not Started | Not Merged | Independent of both other streams from Day 1
feature/c/notifications/channel-adapters | Developer A | Not Started | Not Merged | Independent scaffolding; handlers wired once producer events exist